## Staff
Type | Migration | MDM | Category | Trust Feedback | IT Work | Licenses Migration Costs | Notes
Domain Name Change | Yes | 365 | 365 Domain Name Audit |  |  | IT Admin | SFET
365 Distrbution Lists | Waiting Feedback | 365 | 365 Group Audit | Trust to advise DL's to keep, this allow housekeeping | We provide a list of DL's | Powershell | Confirmation of live DL's
365 External Distribution Lists | Waiting Feedback | 365 | 365 Group Audit | Trust to advise external DL's to keep, this allow housekeeping | We provide a list of External DL's | Powershell | These are re-created during the SharePoint migration
365 Security Groups | Waiting Feedback | 365 | 365 Group Audit | N/A | Created as part of the migration | Powershell | These are re-created during the SharePoint migration
365 Teams Groups | Waiting Feedback | 365 | 365 Group Audit | Trust to advise Teams groups to keep, this allow housekeeping | We provide a list of Teams groups | Powershell
365 Shared Mailboxes | Waiting Feedback | 365 | 365 Shared Mailboxes Audit | Trust to advise Shared Mailboxes to keep, this allow housekeeping | We provide a list of Shared Mailboxes | 3rd Party Tool
Legacy Staff Mailboxes | Waiting Feedback | 365 | 365 Shared Mailboxes Audit | Trust to advise Legacy Mailboxes to keep, this allow housekeeping | We provide a list of Legacy Mailboxes | 3rd Party Tool | Typically converted to shared mailboxes and migrated
365 Aliases Addresses | Waiting Feedback | 365 | 365 Staff User Audit | Trust to advise aliases | IT to add aliases as part of migration | Powershell | brightonhill.hants.sch.uk
365 Staff Calendars | Waiting Feedback | 365 | 365 Staff User Audit | Trust to advise if they have specific calendars | IT to provide a list of calendars | 3rd Party Tool
365 Staff OneDrive | Waiting Feedback | 365 | 365 Staff User Audit | Trust to advise what OneDrive migrations to take place | We can provide staff usage to see who is using OneDrive | 3rd Party Tool
365 Staff Users | Waiting Feedback | 365 | 365 Staff User Audit | Trust to advise Staff users to keep, this allow housekeeping | We provide a list of Staff Users | 3rd Party Tool | All passwords will be reset
On-Premises Legacy Staff HomeDrives | Waiting Feedback |  | 365 Staff User Audit | Trust to advise Staff HomeDrives to keep, this allow housekeeping | We provide a list of Staff HomeDrives | SharePoint Agent
On-Permises Staff Users | Waiting Feedback |  | File Structure Audit | Trust to advise Staff Users HomeDrives to keep, this allow housekeeping | We provide a list of Staff User HomeDrives | SharePoint Agent
On-Permises Staff Share | Waiting Feedback |  | File Structure Audit | Trust to advise Staff shared areas to keep, this allow housekeeping | We provide a list of Staff Shared areas | SharePoint Agent
Android Mobiles | No | N/A | List of apps | N/A | N/A | N/A | IT to check if these are being managed on Intune
Android Tablets | No | N/A | List of apps | N/A | N/A | N/A | IT to check if these are being managed on Intune
iPads | No | N/A | List of apps | N/A | N/A | N/A | IT to check if these are being managed on Intune
iPhones | No | N/A | List of apps | N/A | N/A | N/A | IT to check if these are being managed on Intune
iPods | No | N/A | List of apps | N/A | N/A | N/A | IT to check if these are being managed on Intune
Windows Devices | No | N/A | List of apps | N/A | N/A | N/A | IT to check if these are being managed on Intune
Sharepoint Sites | Waiting Feedback |  | SharePoint Audit | Trust to advise SharePoint sites to keep, this allow housekeeping | We provide a list of SharePoint sites | Steve / Lewis / 3rd Party Tool ?
Team Apps | No | 365 | Teams App Audit | N/A | N/A | N/A
Teams SharePoint Sites | Waiting Feedback | 365 | Teams Sites Audit | Trust to advise Team sites sites to keep, this allow housekeeping | We provide a list of Teams sites | Steve / Lewis / 3rd Party Tool ?
Preferred Email Address | Waiting Feedback | 365 | FirstintialLastname@BrightonHill.sfet | Trust to advise preferred email address | IT to action upon migration | Powershell
On-Premise Sync | Yes |  | On-Premises Audit | N/A | IT to perform checks prior to migration | IT Admin

## Data (hidden)
N/A | 365 Aliases Addresses | 365 Domain Name Audit | 365 | 3rd Party Tool
No | 365 Distrbution Lists | 365 Group Audit | Intune | IT Admin
Create | 365 External Distribution Lists | 365 Shared MailBox Audit | Jamf | N/A
Waiting Feedback | 365 Security Groups | 365 Shared Mailboxes Audit | Lightspeed | Powershell
Yes | 365 Shared Mailboxes | 365 Staff User Audit | Meraki | SharePoint Agent
| 365 Staff Calendars | 365 Student User Audit | N/A | Steve / Lewis / 3rd Party Tool ?
| 365 Staff OneDrive | File Structure Audit | On-Premises Exchange | N/A
| 365 Staff Users | List of apps
| 365 Student Calendars | N/A
| 365 Student OneDrive | On-Premises Audit
| 365 Student Users | SharePoint Audit
| 365 Teams Groups | Staff User Audit
| Android Mobiles | Teams App Audit
| Android Tablets | Teams Audit
| Chromebooks | Teams Sites Audit
Domain Name Change
iPads
iPhones
iPods
Legacy Staff Mailboxes
Legacy Student Mailboxes
N/A
On-Permises Staff Share
On-Permises Staff Users
On-Permises Student Share
On-Permises Student Users
On-Premise Sync
On-Premises Legacy Staff HomeDrives
On-Premises Legacy Student HomeDrives
Preferred Email Address
Sharepoint Sites
Team Apps
Teams
Teams SharePoint Sites
Windows Devices

## Students
Type | Migration | MDM | Category | Trust Feedback | IT Work | Licenses Migration Costs | Notes
Domain Name Change | Yes | 365 | 365 Domain Name Audit |  |  | IT Admin | SFET
365 Distrbution Lists | Waiting Feedback | 365 | 365 Group Audit | Trust to advise DL's to keep, this allow housekeeping | We provide a list of DL's | Powershell | Confirmation of live DL's
365 External Distribution Lists | Waiting Feedback | 365 | 365 Group Audit | Trust to advise external DL's to keep, this allow housekeeping | We provide a list of External DL's | Powershell | These are re-created during the SharePoint migration
365 Security Groups | Waiting Feedback | 365 | 365 Group Audit | N/A | Created as part of the migration | Powershell | These are re-created during the SharePoint migration
365 Teams Groups | Waiting Feedback | 365 | 365 Group Audit | Trust to advise Teams groups to keep, this allow housekeeping | We provide a list of Teams groups | Powershell
365 Shared Mailboxes | Waiting Feedback | 365 | 365 Shared Mailboxes Audit | Trust to advise Shared Mailboxes to keep, this allow housekeeping | We provide a list of Shared Mailboxes | 3rd Party Tool
Legacy Student Mailboxes | Waiting Feedback | 365 | 365 Shared Mailboxes Audit | Trust to advise Legacy Mailboxes to keep, this allow housekeeping | We provide a list of Legacy Mailboxes | 3rd Party Tool | Typically converted to shared mailboxes and migrated
365 Aliases Addresses | Waiting Feedback | 365 | 365 Student User Audit | Trust to advise aliases | IT to add aliases as part of migration | Powershell | brightonhill.hants.sch.uk
365 Student Calendars | Waiting Feedback | 365 | 365 Student User Audit | Trust to advise if they have specific calendars | IT to provide a list of calendars | 3rd Party Tool
365 Student OneDrive | Waiting Feedback | 365 | 365 Student User Audit | Trust to advise what OneDrive migrations to take place | We can provide staff usage to see who is using OneDrive | 3rd Party Tool
365 Student Users | Waiting Feedback | 365 | 365 Student User Audit | Trust to advise Staff users to keep, this allow housekeeping | We provide a list of Staff Users | 3rd Party Tool | All passwords will be reset
On-Premises Legacy Student HomeDrives | Waiting Feedback |  | 365 Student User Audit | Trust to advise Staff HomeDrives to keep, this allow housekeeping | We provide a list of Staff HomeDrives | SharePoint Agent
On-Permises Student Users | Waiting Feedback |  | File Structure Audit | Trust to advise Staff Users HomeDrives to keep, this allow housekeeping | We provide a list of Staff User HomeDrives | SharePoint Agent
On-Permises Student Share | Waiting Feedback |  | File Structure Audit | Trust to advise Staff shared areas to keep, this allow housekeeping | We provide a list of Staff Shared areas | SharePoint Agent
Android Mobiles | No | N/A | List of apps | N/A | N/A | N/A | IT to check if these are being managed on Intune
Android Tablets | No | N/A | List of apps | N/A | N/A | N/A | IT to check if these are being managed on Intune
iPads | No | N/A | List of apps | N/A | N/A | N/A | IT to check if these are being managed on Intune
iPhones | No | N/A | List of apps | N/A | N/A | N/A | IT to check if these are being managed on Intune
iPods | No | N/A | List of apps | N/A | N/A | N/A | IT to check if these are being managed on Intune
Windows Devices | No | N/A | List of apps | N/A | N/A | N/A | IT to check if these are being managed on Intune
Sharepoint Sites | Waiting Feedback |  | SharePoint Audit | Trust to advise SharePoint sites to keep, this allow housekeeping | We provide a list of SharePoint sites | Steve / Lewis / 3rd Party Tool ?
Team Apps | No | 365 | Teams App Audit | N/A | N/A | N/A
Teams SharePoint Sites | Waiting Feedback | 365 | Teams Sites Audit | Trust to advise Team sites sites to keep, this allow housekeeping | We provide a list of Teams sites | Steve / Lewis / 3rd Party Tool ?
Preferred Email Address | Waiting Feedback | 365 | FirstintialLastname@BrightonHill.sfet | Trust to advise preferred email address | IT to action upon migration | Powershell
On-Premise Sync | Yes |  | On-Premises Audit | N/A | IT to perform checks prior to migration | IT Admin